# Quorum - UX Brief

Directions: Copy the template into your own folder. Replace the project name and remove any grey italic text as each section gets filled out.

The purpose of this document is to describe the UX request at a high-level. The document will be used to aid in planning and prioritization of the request. See the planning phase of the IDCG Design Process for more information.

## 1. Project at-a-glance

| Author of this document | Skip Hanson |
| --- | --- |
| Date of last update | 3/27/2024 |
| Project Name | [Enter the project name exactly as it appears in the PRFAQ] |
| Intake ticket | https://app.asana.com/read-only/Guardian/8442528107068/cddfe3814d6a28fae7c8295284d993fd/list |
| Domain Group | Governance |
| High-level description | Quorum is a security-base feature that allows for the creation of member groups that have the responsibilty to approve or reject certain critical actions on service resources. |
| Requested by | @[name] |
| Submitted on behalf of | @[name] |
| Target launch date | ReInvent 2024 |
| Scope | Large |
| Slack channel(s) | https://amazon.enterprise.slack.com/archives/C05S9H0TP2L |
| Reference documents |  |
| Asana Project | https://app.asana.com/0/1204283280840265/1204283191405646 |
| PRFAQ | Enter link |
| Metrics plan | Enter link |
| Stakeholders |  |
| Product lead (PMT) | Raman Gupta |
| Program management (TPM) | Raman Gupta, Alex Merida |
| Service team SDM | Anupam Kalkarni |
| Console SDM |  |
| Eng lead | Marcin Fraczak |
| UX designer | Skip Hanson |
| UX researcher | Skip Hanson |
| Tech writer |  |

## 2. Schedule and effort estimates

Estimates are high-level and based on the current understanding of project requirements at the time of writing this document. Estimates should be in effective design weeks and may not be consecutive (i.e. work may start and stop but effectively will take a total of 3 weeks).

UX estimated start date: [mm/dd/yyyy]

Date engineering needs designs:  03/15/2024 Portal, 04/31/2024 Quorum admin.

| 1 | Effort | Weeks | Estimated completion date (ECD) |  |  |
| --- | --- | --- | --- | --- | --- |
| 2 | Directional designs |  |  |  |  |
| 3 | Participant portal | 1 week | 3/1/2024 |  |  |
| 4 | Dev sign-off - Participant portal |  | 3/15/2024 |  |  |
| 5 | PM guided customer conversations |  | 4/5/2024 |  |  |
| 6 | Quorum admin - Group creation | 1 weeks | 4/5/2024 |  |  |
| 7 | Quorum admin - group edit and delete | 2 weeks | 4/19/2024 |  |  |
| 8 | Quorum admin home + enablement flows | 2 weeks | 5/6/2024 |  |  |
| 9 | Dev sign-off - Quorum admin |  | 5/3/2024 |  |  |
| 10 | In service - Quorum group selection & developer experience | 2 weeks | TBD | Will be completed by Backup UX |  |
| 11 | UX Milestones Deep dive | 1 week | 5/10/2024 |  |  |
| 12 | Prepare presentation |  | 5/10/2024 |  |  |
| 13 | Review |  |  |  |  |
| 14 | User research |  | 7/12/2024 |  |  |
| 15 | Planning | 1 week | 5/17/2024 |  |  |
| 16 | Recruiting & prototypying | 2 weeks | 6/10/2024 |  |  |
| 17 | Testing | 1 week | 6/17/2024 | Had to go two weeks due to long sessions and UT issues. |  |
| 18 | Detailed designs | 1 week | 6/14/2024 |  |  |
| 19 | Quorum email templates for Group invites and action requests |  |  |  |  |
| 20 | Final interactions |  |  |  |  |
| 21 | Doc review |  | 6/1/2024 |  |  |
| 22 | Final reviews |  |  |  |  |
| 23 | Identity & Governance & Backup leadership review | 1 week | 6/21/2024 |  |  |
| 24 | UX Milestones sign-off | 1 week | 6/26/2024 |  |  |
| 25 |  |  |  |  |  |
| 26 | Fit and finish |  |  |  |  |
| 27 | Fit and finish pre-check |  |  |  |  |
| 28 | UXDR fit and finish review |  |  |  |  |
| 29 | Launch |  |  |  |  |
| 30 | Console tagging |  |  |  |  |
| 31 | Launch |  |  |  |  |
| 32 | Darkroom reporting |  |  |  |  |

## 3. Tracking

Quorum UX Design Tracking

## 4. UX narrative (problem and solution)

Frame the problem in the light of the humans it will touch. The PR/FAQ can be used as inspiration but the content here should be rephrased in a way that you can articulate yourself. This will help challenge your own understanding and validate it with stakeholders who will review this brief.

Enter a 2-3 sentence narrative summarizing the primary experience the project is targeting to engage with. Example:

“Jim is an application user that represents a large group of data scientists within his company. He consistently needs access to Amazon SageMaker to perform data analysis on data that resides in Amazon Redshift clusters. ”

Include 2-3 paragraphs of a clear narrative telling the story of how the new UX will change/improve the user(s) experience. You may sample from the PR in the PR/FAQ, however you should attempt to phrase this more specific to the actual UI the customer will interact with. Even if this changes in the future (and it most likely will after this brief is completed), you will have established a narrative you can evolve. It’s important you can use this narrative (fake names, scenarios through your UX and through your presentations and socializing). Use your discretion, on length necessary to tell the story.

## 5. User personas

These are the primary personas that will be directly influenced by the project release. Add or remove rows if your project is touching less or more personas. The Persona title can be modified to fit your project more specifically. For example, IT professional can be “Identity Center admin” when working on that service. The avatar names should be used in your narratives and follow-through your UX mockups and demos. Add a priority ‘Primary’ vs. ‘Secondary’ to identify those personas that will be most impacted. The primary goal should be a 1-2 sentence goal the personas has specific to the service and something that the project will address. Lastly, the ‘Primary opportunity from project’ should include a 1-2 sentence statement providing the key benefit the persona will take away from the experience. This is something that can be a cornerstone of your UX focus and socializing with others.

Persona resources:  AWS Identity Personas | AWS personas

| Image | Persona | Avatar name | Priority | Primary goal | Primary opportunity from project |
| --- | --- | --- | --- | --- | --- |
|  | IT professional | Kelly | Primary | [1-2 sentences, ex: Maintain high-velocity in AWS app enablements and reduce complexities in app access.] | [1-2 sentences, ex: User/groups are provided access through verifiable tokens either though a trusted client or through programmatic access using trusted token issuers.] |
|  | Business owner | Erin | Primary | [1-2 sentences] | [1-2 sentences] |
|  | Business user | Jim | Secondary | [1-2 sentences] | [1-2 sentences] |
|  | Cloud architect | Sarah | Secondary | [1-2 sentences] | [1-2 sentences] |
|  | Dev Operations | Phill |  | [1-2 sentences] | [1-2 sentences] |
|  | Developer | Tailor |  | [1-2 sentences] | [1-2 sentences] |
|  | IT Leader | Sam |  | [1-2 sentences] | [1-2 sentences] |

## 5. Research needs

### 4.1. UX research needs

- Customer interviews

- Metrics / data reporting

- Usability testing

### 4.2. Description of needs

Customer study with IdC customers and launch partners of S3....

# Alternate schedules considered

### Approach 2: Participant Portal & Quorum as two separate design projects. User research and all reviews will be separate.

Participant portal ECD: 4/26/2024

Quorum ECD: 7/26/2024

| 1 | Effort | Weeks | Completion dates |
| --- | --- | --- | --- |
| 2 | Designs |  |  |
| 3 | Participant portal | 1 week | 3/1/2024 |
| 4 | UX Milestones Deep Dive | 2 weeks | 3/15/2024 |
| 5 | Prepare presentation |  |  |
| 6 | Review |  |  |
| 7 | User research |  |  |
| 8 | Planning | 1 week | 3/22/2024 |
| 9 | Recruiting & prototypying | 1 week | 3/29/2024 |
| 10 | Testing | 1 week | 4/5/2024 |
| 11 | Detailed designs | 1 week | 4/12/2024 |
| 12 | Detailed designs including doc review |  |  |
| 13 | Final alignment with stakeholders |  |  |
| 14 | Approvals and sign-off |  |  |
| 15 | Identity & Governance leadership review | 1 week | 4/19/2024 |
| 16 | UX Milestones Sign-off | 1 week | 4/26/2024 |
| 17 | Fit and finish |  |  |
| 18 | Fit and finish pre-check |  |  |
| 19 | UXDR fit and finish review |  |  |
| 20 | Launch |  |  |
| 21 | Console tagging |  |  |
| 22 | Launch |  |  |
| 23 | Darkroom reporting |  |  |
| 24 |  |  |  |
| 25 | Designs |  |  |
| 26 | Quorum admin - Group creation | 2 weeks | 5/10/2024 |
| 27 | Quorum admin - Enablement flows | 2 weeks | 5/24/2024 |
| 28 | Quorum admin - In-service guidance | 1 week | 5/31/2024 |
| 29 | UX Milestones Deep dive | 2 weeks | 6/14/2024 |
| 30 | Prepare presentation |  |  |
| 31 | Review |  |  |
| 32 | User research |  |  |
| 33 | Planning | 1 week | 6/21/2024 |
| 34 | Recruiting & prototypying | 1 week | 6/28/2024 |
| 35 | Testing | 1 week | 7/5/2024 |
| 36 | Detailed designs | 1 week | 7/12/2024 |
| 37 | Detailed designs including doc review |  |  |
| 38 | Final alignment with stakeholders |  |  |
| 39 | Approvals and sign-off |  |  |
| 40 | Identity & Governance leadership review | 1 week | 7/19/2024 |
| 41 | UX Milestones Sign-off | 1 week | 7/26/2024 |

### Approach 3: User test separately for Portal & Quorum but take them both through final reviews together.

ECD: 7/5/2024

| 1 | Effort | Estimate (business weeks) (remaining) | Dates |
| --- | --- | --- | --- |
| 2 | Designs |  |  |
| 3 | Participant portal | 1 week | 3/1/2024 |
| 4 | User research |  |  |
| 5 | Planning | 1 week | 3/8/2024 |
| 6 | Recruiting & prototypying | 1 week | 3/15/2024 |
| 7 | Testing | 1 week | 3/22/2024 |
| 8 | Incorporate insights from user testing | 1 week | 3/29/2024 |
| 9 |  |  |  |
| 10 | Design |  |  |
| 11 | Quorum admin - Group creation | 2 weeks | 4/12/2024 |
| 12 | Quorum admin - Enablement flows | 2 weeks | 4/26/2024 |
| 13 | Quorum admin - In-service guidance | 1 week | 5/3/2024 |
| 14 | User research |  |  |
| 15 | Planning | 1 week | 5/10/2024 |
| 16 | Recruiting & prototypying | 1 week | 5/17/2024 |
| 17 | Testing | 1 week | 5/24/2024 |
| 18 | Incorporate insights from user testing | 1 week | 5/31/2024 |
| 19 |  |  |  |
| 20 | UX Milestones Deep dive | 2 weeks | 6/7/2024 |
| 21 | Prepare presentation |  |  |
| 22 | Review |  |  |
| 23 | Detailed designs | 1 week | 6/21/2024 |
| 24 | Detailed designs including doc review |  |  |
| 25 | Final alignment with stakeholders |  |  |
| 26 | Approvals and sign-off |  |  |
| 27 | Identity & Governance leadership review | 1 week | 6/28/2024 |
| 28 | UX Milestones sign-off | 1 week | 7/5/2024 |

### UX review notes

Quorum UX review notes4/5